## Gap Analysis (hidden)
Yakult - SFA Gap Analysis
Date | Notes | Type | Category | CR Priorioty | Est Man Days Efforts
2023-09-20 | TBC | Gap | Integration | P1 | TBC
2023-09-20 | TBC | Gap | Van Sales Order | P1 | TBC
2023-09-20 | TBC | Gap | Van Goods Return | P1 | TBC
2023-09-20 | TBC | Gap | Van Goods Request | P1 | TBC
2023-09-20 | TBC | Gap | Van Stock Count | P1 | TBC
2023-09-20 | TBC | Gap | End of Day | P1 | TBC

## Project Gantt Chart
SFA DMS Project Plan |  |  |  | 45428 | 45429 | 45432 | 45433 | 45434 | 45435 | 45436 | 45439 | 45440 | 45441 | 45442 | 45443 | 45446 | 45447 | 45448 | 45449 | 45450 | 45453 | 45454 | 45455 | 45456 | 45457 | 45460 | 45461 | 45462 | 45463 | 45464 | 45467 | 45468 | 45469 | 45470 | 45471 | 45474 | 45475 | 45476 | 45477 | 45478 | 45481 | 45482 | 45483 | 45484 | 45485 | 45488 | 45489 | 45490 | 45491 | 45492 | 45495 | 45496 | 45497 | 45498 | 45499 | 45502 | 45503 | 45504 | 45505 | 45506 | 45509 | 45510 | 45511 | 45512 | 45513 | 45516 | 45517 | 45518 | 45519 | 45520 | 45523 | 45524 | 45525 | 45526 | 45527 | 45530 | 45531 | 45532 | 45533 | 45534 | 45537 | 45538 | 45539 | 45540 | 45541 | 45544 | 45545 | 45546 | 45547 | 45548 | 45551 | 45552 | 45553 | 45554 | 45555 | 45558 | 45559 | 45560 | 45561 | 45562 | 45565 | 45566 | 45567 | 45568 | 45569 | 45572 | 45573 | 45574 | 45575 | 45576 | 45579 | 45580 | 45581 | 45582 | 45583 | 45586 | 45587 | 45588 | 45589 | 45590 | 45593 | 45594 | 45595 | 45596 | 45597 | 45600 | 45601 | 45602 | 45603 | 45604 | 45607 | 45608 | 45609 | 45610 | 45611 | 45614 | 45615 | 45616 | 45617 | 45618 | 45621 | 45622 | 45623 | 45624 | 45625 | 45628 | 45629 | 45630 | 45631 | 45632 | 45635 | 45636 | 45637 | 45638 | 45639 | 45642 | 45643 | 45644 | 45645 | 45646 | 45649 | 45650 | 45651 | 45652 | 45653 | 45656 | 45657 | 45658 | 45659 | 45660 | 45663 | 45664 | 45665 | 45666 | 45667 | 45670 | 45671 | 45672 | 45673 | 45674 | 45677 | 45678 | 45679 | 45680 | 45681 | 45684 | 45685 | 45686 | 45687 | 45688 | 45691 | 45692 | 45693 | 45694 | 45695 | 45698 | 45699 | 45700 | 45701 | 45702 | 45705 | 45706 | 45707 | 45708 | 45709 | 45712 | 45713 | 45714 | 45715 | 45716 | 45719 | 45720 | 45721 | 45722 | 45723 | 45726 | 45727 | 45728 | 45729 | 45730 | 45733 | 45734 | 45735 | 45736 | 45737 | 45740 | 45741 | 45742 | 45743 | 45744 | 45747 | 45748 | 45749 | 45750 | 45751 | 45754 | 45755 | 45756 | 45757 | 45758 | 45761 | 45762 | 45763 | 45764 | 45765 | 45768 | 45769 | 45770 | 45771 | 45772 | 45775 | 45776 | 45777 | 45778 | 45779 | 45782 | 45783 | 45784 | 45785 | 45786 | 45789 | 45790 | 45791 | 45792 | 45793 | 45796 | 45797 | 45798 | 45799 | 45800 | 45803 | 45804 | 45805 | 45806
|  |  |  | 2024-05-16 |  |  |  |  | 2024-05-23 |  |  |  |  | 2024-05-30 |  |  |  |  | 2024-06-06 |  |  |  |  | 2024-06-13 |  |  |  |  | 2024-06-20 |  |  |  |  | 2024-06-27 |  |  |  |  | 2024-07-04 |  |  |  |  | 2024-07-11 |  |  |  |  | 2024-07-18 |  |  |  |  | 2024-07-25 |  |  |  |  | 2024-08-01 |  |  |  |  | 2024-08-08 |  |  |  |  | 2024-08-15 |  |  |  |  | 2024-08-22 |  |  |  |  | 2024-08-29 |  |  |  |  | 2024-09-05 |  |  |  |  | 2024-09-12 |  |  |  |  | 2024-09-19 |  |  |  |  | 2024-09-26 |  |  |  |  | 2024-10-03 | 2024-10-04 |  |  |  |  | 2024-10-11 |  |  |  |  | 2024-10-18 |  |  |  |  | 2024-10-25 |  |  |  |  | 2024-11-01 |  |  |  |  | 2024-11-08 |  |  |  |  | 2024-11-15 |  |  |  |  | 2024-11-22 |  |  |  |  | 2024-11-29 |  |  |  |  | 2024-12-06 |  |  |  |  | 2024-12-13 |  |  |  |  | 2024-12-20 |  |  |  |  | 2024-12-27 |  |  |  |  | 2025-01-03 |  |  |  |  | 2025-01-10 |  |  |  |  | 2025-01-17 |  |  |  |  | 2025-01-24 |  |  |  |  | 2025-01-31 |  |  |  |  | 2025-02-07 |  |  |  |  | 2025-02-14 |  |  |  |  | 2025-02-21 |  |  |  |  | 2025-02-28 |  |  |  |  | 2025-03-07 |  |  |  |  | 2025-03-14 |  |  |  |  | 2025-03-21 |  |  |  |  | 2025-03-28 |  |  |  |  | 2025-04-04 |  |  |  |  | 2025-04-11 |  |  |  |  | 2025-04-18 |  |  |  |  | 2025-04-25 |  |  |  |  | 2025-05-02 |  |  |  |  | 2025-05-09 |  |  |  |  | 2025-05-16 |  |  |  |  | 2025-05-23
Activity | Start | Finish | Duration | 45428: 2024-05-16; 45432: 2024-05-20; 45434: 2024-05-22; 45436: 2024-05-24; 45440: 2024-05-28; 45442: 2024-05-30; 45446: 2024-06-03; 45448: 2024-06-05; 45450: 2024-06-07; 45454: 2024-06-11; 45456: 2024-06-13; 45460: 2024-06-17; 45462: 2024-06-19; 45464: 2024-06-21; 45468: 2024-06-25; 45470: 2024-06-27; 45474: 2024-07-01; 45476: 2024-07-03; 45478: 2024-07-05; 45482: 2024-07-09; 45484: 2024-07-11; 45488: 2024-07-15; 45490: 2024-07-17; 45492: 2024-07-19; 45496: 2024-07-23; 45498: 2024-07-25; 45502: 2024-07-29; 45504: 2024-07-31; 45506: 2024-08-02; 45510: 2024-08-06; 45512: 2024-08-08; 45516: 2024-08-12; 45518: 2024-08-14; 45520: 2024-08-16; 45524: 2024-08-20; 45526: 2024-08-22; 45530: 2024-08-26; 45532: 2024-08-28; 45534: 2024-08-30; 45538: 2024-09-03; 45540: 2024-09-05; 45544: 2024-09-09; 45546: 2024-09-11; 45548: 2024-09-13; 45552: 2024-09-17; 45554: 2024-09-19; 45558: 2024-09-23; 45560: 2024-09-25; 45562: 2024-09-27; 45566: 2024-10-01; 45569: 2024-10-04; 45573: 2024-10-08; 45575: 2024-10-10; 45579: 2024-10-14; 45581: 2024-10-16; 45583: 2024-10-18; 45587: 2024-10-22; 45589: 2024-10-24; 45593: 2024-10-28; 45595: 2024-10-30; 45597: 2024-11-01; 45601: 2024-11-05; 45603: 2024-11-07; 45607: 2024-11-11; 45609: 2024-11-13; 45611: 2024-11-15; 45615: 2024-11-19; 45617: 2024-11-21; 45621: 2024-11-25; 45623: 2024-11-27; 45625: 2024-11-29; 45629: 2024-12-03; 45631: 2024-12-05; 45635: 2024-12-09; 45637: 2024-12-11; 45639: 2024-12-13; 45643: 2024-12-17; 45645: 2024-12-19; 45649: 2024-12-23; 45651: 2024-12-25; 45653: 2024-12-27; 45657: 2024-12-31; 45659: 2025-01-02; 45663: 2025-01-06; 45665: 2025-01-08; 45667: 2025-01-10; 45671: 2025-01-14; 45673: 2025-01-16; 45677: 2025-01-20; 45679: 2025-01-22; 45681: 2025-01-24; 45685: 2025-01-28; 45687: 2025-01-30; 45691: 2025-02-03; 45693: 2025-02-05; 45695: 2025-02-07; 45699: 2025-02-11; 45701: 2025-02-13; 45705: 2025-02-17; 45707: 2025-02-19; 45709: 2025-02-21; 45713: 2025-02-25; 45715: 2025-02-27; 45719: 2025-03-03; 45721: 2025-03-05; 45723: 2025-03-07; 45727: 2025-03-11; 45729: 2025-03-13; 45733: 2025-03-17; 45735: 2025-03-19; 45737: 2025-03-21; 45741: 2025-03-25; 45743: 2025-03-27; 45747: 2025-03-31; 45749: 2025-04-02; 45751: 2025-04-04; 45755: 2025-04-08; 45757: 2025-04-10; 45761: 2025-04-14; 45763: 2025-04-16; 45765: 2025-04-18; 45769: 2025-04-22; 45771: 2025-04-24; 45775: 2025-04-28; 45777: 2025-04-30; 45779: 2025-05-02; 45783: 2025-05-06; 45785: 2025-05-08; 45789: 2025-05-12; 45791: 2025-05-14; 45793: 2025-05-16; 45797: 2025-05-20; 45799: 2025-05-22; 45803: 2025-05-26; 45805: 2025-05-28
Briefing | 2024-05-16 | 2024-05-16 | 1
Briefing of AO (Web/Mobile) | 2024-05-16 | 2024-05-16 | 1
Phase 1 Implementation | 2024-05-30 | 2024-06-06 | 6
Export Danone Master Data | 2024-05-30 | 2024-06-05 | 5
Import Danone Master Data in Datanory DMS | 2024-06-05 | 2024-06-06 | 2
Create New DMS Organization | 2024-06-05 | 2024-06-05 | 1
Phase 2 Testing | 2024-06-07 | 2024-06-14 | 6
Datanory DMS Testing Environment Setup | 2024-06-07 | 2024-06-10 | 2
AO Historical Data Import and Testing | 2024-06-11 | 2024-06-13 | 3
Identifying Gaps | 2024-06-14 | 2024-06-14 | 1
Phase 3 Comparison | 2024-05-21 | 2024-06-07 | 14
Compare Datanory DMS and AO (Web) | 2024-05-21 | 2024-05-30 | 8
Picking List Automation | 2024-05-31 | 2024-06-05 | 4
Compile into PPX | 2024-06-06 | 2024-06-07 | 2
Phase 4 Implementation | 2024-06-28 | 2024-06-30 | 1
Final Checking & Testing Datanory DMS | 2024-06-28 | 2024-06-30 | 1
Phase 5 Presentation | 2024-07-01 | 2024-07-01 | 1
Presentation | 2024-07-01 | 2024-07-01 | 1
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Edit data

## Project Plan
Datanory DMS (Danone) > Data Entry
Module | Activity | Mandays | Start Date | End Date
Briefing | Briefing of AO (Web/Mobile) | 1 | 2024-05-16 | 2024-05-16
Phase 1 Implementation | Export Danone Master Data | 5 | 2024-05-30 | 2024-06-05
Phase 1 Implementation | Create New DMS Organization | 1 | 2024-06-05 | 2024-06-05
Phase 1 Implementation | Import Danone Master Data in Datanory DMS | 2 | 2024-06-05 | 2024-06-06
Phase 2 Testing | Datanory DMS Testing Environment Setup | 2 | 2024-06-07 | 2024-06-10
Phase 2 Testing | AO Historical Data Import and Testing | 3 | 2024-06-11 | 2024-06-13
Phase 2 Testing | Identifying Gaps | 1 | 2024-06-14 | 2024-06-14
Phase 3 Comparison | Compare Datanory DMS and AO (Web) | 8 | 2024-05-21 | 2024-05-30
Phase 3 Comparison | Picking List Automation | 4 | 2024-05-31 | 2024-06-05
Phase 3 Comparison | Compile into PPX | 2 | 2024-06-06 | 2024-06-07
Phase 4 Implementation | Final Checking & Testing Datanory DMS | 1 | 2024-06-28 | 2024-06-30
Phase 5 Presentation | Presentation | 1 | 2024-07-01 | 2024-07-01
Formulas:
Mandays = NETWORKDAYS([Start Date], [End Date])

## Master Data
Row Labels | Min of Start Date | Max of End Date | Sum of Mandays
Briefing | 2024-05-16 | 2024-05-16 | 1
Briefing of AO (Web/Mobile) | 2024-05-16 | 2024-05-16 | 1
Phase 1 Implementation | 2024-05-30 | 2024-06-06 | 8
Export Danone Master Data | 2024-05-30 | 2024-06-05 | 5
Import Danone Master Data in Datanory DMS | 2024-06-05 | 2024-06-06 | 2
Create New DMS Organization | 2024-06-05 | 2024-06-05 | 1
Phase 2 Testing | 2024-06-07 | 2024-06-14 | 6
Datanory DMS Testing Environment Setup | 2024-06-07 | 2024-06-10 | 2
AO Historical Data Import and Testing | 2024-06-11 | 2024-06-13 | 3
Identifying Gaps | 2024-06-14 | 2024-06-14 | 1
Phase 3 Comparison | 2024-05-21 | 2024-06-07 | 14
Compare Datanory DMS and AO (Web) | 2024-05-21 | 2024-05-30 | 8
Picking List Automation | 2024-05-31 | 2024-06-05 | 4
Compile into PPX | 2024-06-06 | 2024-06-07 | 2
Phase 4 Implementation | 2024-06-28 | 2024-06-30 | 1
Final Checking & Testing Datanory DMS | 2024-06-28 | 2024-06-30 | 1
Phase 5 Presentation | 2024-07-01 | 2024-07-01 | 1
Presentation | 2024-07-01 | 2024-07-01 | 1
This page contains the Pivot table necessary for Gantt chart. Please do not remove or edit.

## Sheet1
Master Data to be Export from AO
1 | Customer
2 | SKU
3 | User
4 | Competitor SKU
5 | Distributor
6 | KPI
7 | Warehouse
8 | Trade Promotion
9 | Route Plan

## Comparison (hidden)
Topic | AO | Datanory
| AO Mobile (Seller App) don't have gps tracking to track Salesman location | Datanory Mobile requires salesman to Check In / Check Out to capture their GPS location and time stamp.
| Sales Target is by Sales Order, not sync to Invoice | Sales Target is by Invoice
| MSBI integrate Sales Order from AO that's already delivered, unable to view Invoice in MSBI | MSBI able to integrate Invoice from Datanory since
| Mobile App homepage displays OOS information | Mobile App homepage displays Sales Target, Invoice, Achievement, and Customer List
| 1 Distributor ID can only have 1 Warehouse | 1 Distributor ID can have multiple Warehouse
| AO have 3 Web Portal: Admin, Sales Portal, Distributor Portal | Datanory only have 1 Portal with same address but different login with different access for Admin, Sales Manager, and Distributor
| AO unable to arrange sequence in Route Plan | Datanory allow Supervisor to arrange the sequence for Salesman Route Plan
| AO Mobile App is Online Mode which might cause Salesman to face difficulties while making sales transaction in remote/rural area. | Datanory Mobile App is Offline Mode which allow Salesman to conduct sales activity in remote/rural area where Internet connection is weak
| Salesman unable to access Customer Transaction from Route Plan in Mobile App. Salesman have to go to Customer List instead to do Sales Transaction | Sales able to access Customer details and Transaction from Route Plan list in Mobile App.
| AO have several module that are not in use, but unable to remove or hide | Datanory have the flexibility to hide those unnecessary module that are not in use
| All SKU is showing in Mobile App which cause difficulties to Salesman to select SKU for Stock Replenishment (SO) | Datanory allow user to setup SKU Listing by Customer Level through Chain and Product Category
| AO able to store Competitor SKU, AO allow Admin to upload Competitor Sales Data in Portal | Currently Datanory unable to cater to Competitor SKU
Scanned Sales | Admin able to upload Sales Data into AO, however this usually cause discrepancies. Data manually uploaded and MSBI will not tally. | Currently Datanory don't have Scan Sales in Web. However, Datanory posses Scan Sales Module in Mobile level.
DB Optimization | Currently AO is using 2 servers. 1 is DDM DB which used for Tiger data transit, scanned sales source and competitor product source. Another 1 is DB for distributor to access the report. | By using Datanory, user able to eliminate the cost of 2 servers since Datanory host by MCC. MCC will directly handle report from MSBI to Dapp for Distributor.
| AO able to capture Sell In price | Datanory unable to capture Sell In price
DB Optimization | AO performance is low, the server performance will spike everytime user pull a report. MCC unable to optimize the application. | Datanory performance is optimized, since is developed in-house by MCC and source code is solely managed by MCC
| AO have Leave Application List for Supervisor to fill in for their Salesman. Thus, KPI for plan visit will be excluded for Sick Leave. | Currently Datanory don't have Leave Application Module.
| AO able to create Trade Promotion | Datanory (Suntory Version) have the Promotion Mechanism to cater same as AO
| AO allow Admin to confirm the delivery when the stock is out for delivery | Datanory doesn't support Proof of Delivery
| AO allow Salesman to request for Sample Request and Approved by Admin | Datanory doesn't support Sample Request at the moment. Propose user to create a separate SKU with Sample Remark and Price is RM0.
| AO have Announcement Module to Sales Team and Retailer. However, we assume that Annoucement to Retailer is not in use. | Through Datanory, user able to create announcement for Sales Team
| Danone require to capture KPI Data such as Hit Rate, Price Check, Photo Taking, and Capture Sell Out | Datanory will be able to create KPI Hit Rate, Price Check KPI, KPI for Photo Taking, KPI to Capture Sell Out